Contents

1.  	Introduction								5

2.	Strategic objectives and themes 2011 - 2015			5

3.	Monitoring performance						6

4.	Commitments and 2012/13 milestones				7

5.  	Other corporate business plan commitments and targets	14

Appendix 1 – Our resources for 2012/13					18

1.	INTRODUCTION

This business plan 2012 – 2013 sets out what the Department for Social Development plans to achieve over the next 12 months, aligning with the Programme for Government, our corporate plan 2011 – 2015 and budget allocation.

A report on our achievements during 2011 – 2012 is published on the internet at www.dsdni.gov.uk.

2.	STRATEGIC OBJECTIVES AND THEMES 2011 - 2015

Three Strategic themes: Housing, Welfare Reform and Strengthened Communities and Vibrant Urban Areas represent our Minister’s priorities.  These also provide the broad framework for the commitments and milestones we have set to signpost progress towards achieving our objectives to:

- provide access to decent, affordable, sustainable homes and housing support services;

- meet the needs of the most vulnerable by tackling disadvantage through a transformed social welfare system, the provision of focused support to the most disadvantaged areas and encouraging social responsibility; and

- bring divided communities together by creating urban centres which are sustainable, welcoming and accessible to live, work and relax in peace.

This Plan does not attempt to cover all aspects of our business activities but provides the key commitments and milestones which set the framework for the development of more detailed plans in business areas and which in turn inform the Personal Performance Agreements for individual members of staff.

- MONITORING PERFORMANCE

The Department’s Management Board is responsible for overseeing the delivery of this Business Plan.  The Board and the Minister receive quarterly performance reports which set out progress against all the commitments and milestones identified in Section 4.  This includes a report on performance against delivery of our Savings Delivery Plans which are published separately on our Intranet site www.dsdni.gov.uk.

- COMMITMENTS 2011 – 2015 AND MILESTONES FOR 2012/13

| Strategic Theme - Housing |
| --- |
| Commitments | 2012/13 Milestone |
| Deliver 8,000 social and affordable homes | 1325 Social, and 500 affordable homes delivered |
| Introduce and support a range of initiatives aimed at reducing fuel poverty across Northern Ireland including preventative interventions | 9,000 homes improved Develop programme of initiatives |
| Improve thermal efficiency of Housing Executive stock and ensure full double glazing in its properties. (Housing Executive to bring forward a strategy to improve the thermal efficiency of their housing stock including a programme aimed at providing full double glazing by 2014/15) | Implement programme from 1 April 2012 |
| By the end of 2014/15, to have implemented new structures to support the improved delivery of housing services to the citizens of Northern Ireland | To develop and consult on service delivery structures and develop implementation programme |
| Develop and consult on a new Northern Ireland Housing Strategy | Publish a Housing Strategy for wider consultation in late Spring 2012 |
| To assist vulnerable people to live independently | 17,000 people assisted |
| Reduction in the number of social homes failing to meet the agreed standard for social homes | Set reduction target in late 2012 when 2012 House conditions Survey is received |
| A better regulated Private Rented Sector more capable of meeting housing need | By November 2012 landlord registration and tenancy deposits schemes provided for in Regulations approved by the Assembly Development of appropriate systems to enable the above schemes to be operational in 2013 |

| Strategic Theme - welfare reform |
| --- |
| Commitments | 2012/13 Milestone(s) |
| Reform the welfare system to tackle the root causes of poverty and mitigate against the negative impact of individual reforms | By the end of March 2013, have primary legislation in place to enable reform of the welfare system By March 2013, have developed a new delivery model for a Discretionary Payment Scheme in Northern Ireland to support implementation of the new service from April 2013 By March 2013 to have agreed the operating model for the launch of Universal Credit By March 2013 to have agreed the delivery model for Personal Independence Payment |
| Percentage increase in those working age customers in receipt of work focused benefits or on a support programme to enable them to move into work | To have reassessed 50,000 customers (of the 76,000) claiming incapacity benefit |
| Provide services that encourage family based child maintenance arrangements | By 31 March 2013 to have developed services to support separated and separating parents in line with areas of greatest need identified from the Northern Ireland Child Maintenance population survey |
| Provide information and support for separated and separating families | By 31 March 2013 to have taken forward the recommendations arising from the Child Maintenance Choices customer survey By 31 March 2013 to have increased awareness of the Child Maintenance Choices service |
| Implement a reformed statutory child maintenance system that will be more efficient and will work for both parents, the taxpayer and children | By 31 March 2013 to have introduced Phase 1 of the new statutory Child Maintenance scheme By 31 March 2013 to have commenced preparation for Phase 2 of the new statutory Child Maintenance scheme |

| Strategic Theme - strengthened communities and vibrant urban areas |
| --- |
| Commitment | 2012/13 Milestone(s) |
| Bring forward a new approach to regeneration which will build on what we know works and will aim to improve the effectiveness and efficiency of regeneration and community development investment. The aim is towards a renewed focus on ensuring that regeneration tackles the underlying economic challenges | By 31 December 2012 to have adopted a new Urban Regeneration and Community Development Policy Framework |
| Invest in social enterprise growth to increase sustainability in the broad community sector | By 31 March 2013 to have developed and implemented a Community Asset Transfer Policy Framework across government By March 2013 to continue to provide opportunities to support social enterprise growth through existing programmes |
| Strategic theme - strengthened communities and vibrant urban areas |
| Commitment | 2012/13 Milestone(s) |
| Develop a joined-up approach by the statutory, private and community sectors to maximise the potential regeneration opportunity for Belfast from the expansion of the University of Ulster’s York Street Campus | By 31 March 2013 to have developed a Community and Business Opportunity Plan which will set out actions and milestones to promote the potential regeneration benefits arising from the campus development |
| Reduce the gap between Neighbourhood Renewal Areas and Non-Neighbourhood Renewal Areas on key deprivation indicators relating to health, community safety, education and worklessness; and in addition respond to issues impacting negatively on areas outside Neighbourhood Renewal Areas through our Areas at Risk Programme | By 31 March 2013 to have produced an annual report detailing movement on key deprivation indicators By 31 March 2013 to deliver services to tackle health, community safety, education, worklessness and other inequalities in Neighbourhood Renewal Areas |
| By the end of 2014/15, to introduce a new programme to tackle deprivation and regenerate our most deprived areas | By 31 March 2013, to have completed consultation on a successor programme for Neighbourhood Renewal |
| Strategic theme - strengthened communities and vibrant urban areas |
| Commitment | 2012/13 Milestone(s) |
| Deliver at least 30 schemes to improve landscapes in public areas to promote private sector investment in towns and cities across Northern Ireland | By 31 March 2013 to have delivered10 Public Realm schemes delivered |
| Bring at least 18 Comprehensive Development opportunities to the market for consideration by March 2015 | By 31 March 2013 to have issued development briefs or initiated competitive procurement for 6 further schemes |
| To lever in an average of £6 million of private investment through the Urban Development Grant Scheme | By 31 March 2013 to have made 12 offers in respect of Urban Development Grant schemes |
| Implement a Volunteering Strategy to promote and develop volunteering | By 31 March 2013 to have facilitated the recruitment of 5,000 new volunteers |
| Continue to work with OFMDFM and Ilex on the regeneration of Derry/Londonderry | By 31 March 2013 to have completed the Development Framework and secured outline planning permission/commenced decontamination works at Fort George By 31 March 2013 to have the Vital Venue in place for UK City of Culture 2013 and have delivered the UK City of Culture Infrastructure Fund |

5.	OTHER CORPORATE BUSINESS PLAN COMMITMENTS

The Departmental Management Board will also be monitoring progress on a number of other Corporate Business Plan commitments as set out below:

| Commitment | Target |
| --- | --- |
| Tackling Homelessness | Develop a programme of initiatives following the launch of the NI Housing Executive’s Homelessness Strategy in Spring 2012 |
| Modernise service delivery to improve choice and accessibility for benefit customers | In partnership with the Department of Finance and Personnel, Digital Inclusion Unit, have finalised a programme of digital inclusion activity for the Social Security Agency and implemented a number of pilot exercises across Northern Ireland by March 2013 Have delivered 2 new Jobs and Benefits Offices by March 2013 By May 2012 to have migrated all benefit direct payments to Central Payments System |
| Ensure benefit customers are receiving the right benefit at the right time | Financial Accuracy Income Support - 99% Jobseekers Allowance - 99% State Pension - 99% State Pension Credit - 98% Disability Living Allowance - 99% Employment and Support Allowance - 96% Clearance (days) Income Support - 9 Jobseekers Allowance - 12 State Pension - 8 State Pension Credit - 10 Disability Living Allowance - 37 Employment and support Allowance - 14 |
| Maximise the uptake of benefits by targeting those likely to be eligible for unclaimed benefit | By March 2013, develop and implement a strategy for increasing the uptake of benefits Implement and evaluate the Innovation fund – working in partnership with the Atlantic Philanthropies and 5 third sector partners by March 2013 By March 2013 to have contacted 25,000 customers to offer a full benefit assessment |
| Business Improvement Districts legislation | Enact primary legislation by 31 March 2013 |
| Annual Procurement Plan | Produce the Department’s 2013/14 plan by 31 March 2013 |
| Improve Employee Engagement | Agree an Employee Engagement Strategy and Action Plan by 31 March 2013 |
| Reduce Sickness Absence | No more than 12.1 days lost through absence by 31 March 2013 |
| Effective Resourcing | Ensure that substantive staff in post levels are at least 95 percent of baselined posts throughout the year |
| Refreshed Industrial Relations Framework | By 28 September 2012, implement a refreshed Industrial Relations Framework that will set out the approach to Industrial Relations in the Department |
| Career Development | By September 2012, to have developed a Career Development strategy for the Department to provide career development direction with initiatives being piloted and implemented on a phased approach from 2012 - 2015 |
| Accommodation | By September 2012 agree a new Accommodation strategy to provide the direction of estate management over the next number of years with the emphasis on reducing costs and taking forward business sustainability plans to increase energy efficiency |

Appendix 1 – Our resources for 2012/13

| Spending Area | Current £m | Capital £m | Total £m |
| --- | --- | --- | --- |
| Social Security Administration | 252.7 | 2.7 | 255.5 |
| Dept Work & Pensions Admin Agency Services | 0.4 | - | 0.4 |
| Sub-Total |  |  |  |
|  | 253.1 | 2.7 | 255.8 |
| Child Maintenance and Enforcement Division (NI) Administration | 19.4 | - | 19.4 |
| NI Housing Executive | 189.5 | -32.9 | 156.7 |
| Housing Associations | -0.8 | 115.0 | 114.1 |
| Sub-Total |  |  |  |
|  | 188.7 | 82.1 | 270.8 |
| Urban Regeneration/Community Development | 62.3 | 33.0 | 95.3 |
| EU Peace Programme | 0.3 | 2.6 | 2.9 |
| Sub-Total |  |  |  |
|  | 62.6 | 35.6 | 98.1 |
| Overall Total | 523.7 | 120.4 | 644.1 |

Due to rounding, the sum of individual totals may not match exactly the sub-totals or overall total in the table.

In addition, the Department has been allocated an Annually Managed Expenditure Budget of £5425 million (£5418 million for Social Security Benefit Expenditure and Financial Assistance Scheme and £7 million for Urban Regeneration Non-Cash Costs). The Annually Managed Expenditure Budget is demand led and consequently subject to change throughout the year.

2012/13 Budget is subject to review by the Department.

# Further Information

This Business Plan for 2012–2013 is available on the Internet at www.dsdni.gov.uk.

Copies can also be obtained by writing to:

# Corporate Planning and Governance Unit

4th Floor

Lighthouse Building

1 Cromac Place

Gasworks Business Park

Ormeau Road

Belfast

BT7 2JB

# Or by e-mailing cpgu@dsdni.gov.uk

Corporate Planning and Governance Unit can also be contacted by telephone on 028 9082 9502.

Copies in alternative formats or languages will be considered in light of demand.

# Text boxes

2012-2013